## Slide 1
Lal Shanker Ghimire
Joint Secretary
FACD, Ministry of Finance
Joint Evaluation in Nepal: Experience Sharing from the Paris Declaration Evaluation

## Slide 2: Outline
Process of Initiating PD Evaluation
Positive Lessons Learnt
Challenges
Response to challenges faced

## Slide 3: Process
  Nepal participated in the regional preparatory workshops
  Convened a National Reference Group comprising a wide range of DPs and senior Government Officials.
  MOF coordinated to find support from ADB and UNDP
  A National Evaluation Team formed (led by Joint Secretary, FACD/Ministry of Finance which included 4 officials from FACD, 4 DPs, 1 Civil Society, 3 Consultants, 1 data analyst)

## Slide 4: Process - Continued…
  Main Task was carried out by Consultants and 2 FACD staffs
  NET developed approach papers and methodology during Inception Phase.
  3 core questions and suggested sub questions were discussed at a National Workshop held in April, 2010.
  Workshop identified Nepal specific questions.
  Health Sector was taken as a specific focus study and education sector was taken as second specific sector.
  Specific Questionnaires to the DPs and government officials were designed and forwarded for response
  Quantitative and qualitative data were collected

## Slide 5: Continued….
Face to face interviews were undertaken with DP Heads and Senior Government Officials by at least 2 team members
Focal Group Discussions were conducted (in Kathmandu and in two districts, Banke and Dadeldhura) comprising of academics, civil society, government officials, NGOs and district level DP Officials.
Draft report prepared and circulated among stakeholders and core team members.
Validation meeting was organised with key stakeholders – civil society, private sector, government and DPs
Draft was presented in the 3rd IRG held in Dec, 2010 in Bali
Final version was endorsed by National Reference Group on 16 December, 2010.

## Slide 6: Positive Lessons Learnt
On the aspects of the evaluation process:
Whole process was led by the government (MOF) with the support of consultants – proved as an effective Team Spirit.
Direct Interview Method gave an opportunity to dig out the perception of different stakeholders about the Evaluation.
Very encouraging response received from DPs as well as Government Officials
Focused Group Discussion was very useful at local level, where the participants had an opportunity to understand better the Paris Principles through interaction with the team
Evaluation Process somehow helped create/enhance awareness about aid effectiveness (especially at local level)
Easy to collect required information as both health and education sector were under SWAP since 2004.

## Slide 7: Contd….
Positive findings on Aid Effectiveness practices:
Nepal Portfolio Performance Review done annually.
Local Donor Meeting held periodically
Good progress toward country ownership in preparing and implementing plans and programs
Sector Wide Approach in Health and Education Sector .
Increasing Dialogue between DPs and the Government has built confidence and assertiveness on aid effectiveness issues

## Slide 8: Challenges
  Challenges in the evaluation process
  Written responses not received on specified time. Some specific responses were difficult to get.
  Difficult to arrive at clear conclusions due to subjective judgment, varied levels of understanding and individual perception of the interviewees. Variety of views expressed was difficult to synthesize
  Most participants at the local level were ignorant of the Paris Agenda.
  Difficulty of time management for interviews due to tight evaluation and DP schedules
  Faced queries as to why other sectors beyond health and education were not included in the evaluation process

## Slide 9: Challenges - continued…
Findings on aid effectiveness challenges
Continued Aid Fragmentation with many stand alone projects being implemented directly, direct funding, still a large portion of support coming outside government budget.
Slow progress toward aid predictability.
Weak donor Alignment with country system
Uncoordinated Technical Assistance

## Slide 10: Response to challenges
On aspects of the evaluation process:
Consultants had to use their subjective judgment and managed to discuss with other core team members very frequently to establish trends within a very varied set of responses
At national as well as local level workshops, one session was arranged to highlight Paris Agenda and ensure good understanding before the discussion
Two groups were necessary to conduct interviews whenever the timing collided due to tight schedule

## Slide 11: Contd…
On the aid effectiveness issues raised by the evaluation:
Aid Management Platform operationalised in the Ministry of Finance – access given to all DPs and few Line Ministries to improve transparency and predictability
Joint Action Plan being developed to ensure aid transparency, predictability, use of country systems and discourage PIUs through NPPR mechanism
New Draft Foreign Aid Policy being discussed with stakeholders.

## Slide 12
Thank You