## Slide 1: PISA for Development
Technical Workshops
Project up-date
8th April 2014
OECD Secretariat

## Slide 2: PISA for Development Initial Technical Meeting - Conclusions
Expressed unanimous support for the PISA for Development project
Acknowledged the unique value that PISA has as an international benchmarking tool for quality and equity in schooling and for guiding policies for system improvement.
Agreed a set of next steps for taking the project forward.

## Slide 3: Next steps and actions taken (1)
Next steps | Actions taken
OECD to consult further on and then commission technical papers and to prepare ToR for international contractor | Expert paper on enhancing the descriptive power of PISA cognitive instruments – Ray Adams and John Cresswell Expert paper on enhancing PISA’s contextual questionnaires – Doug Willms and Lucia Tramonte Expert paper on developing methods and approaches for including OOSC in data collection and assessment – Roy Carr-Hill Technical workshops: 8-11 April and June 2014 Expert paper on system level data –UIS Expert paper on other assessment programmes – to be commissioned

## Slide 4: Next steps and actions taken (2)
Next steps | Actions taken
OECD to write to countries with proposed agreement for participation in the project Countries to respond to OECD’s proposed agreement and to confirm their participation Participating countries to nominate NCs and NPMs | OECD has written to Cambodia, Ecuador, Guatemala, Senegal, Sri Lanka and Zambia with proposed agreements Ecuador, Senegal and Zambia have responded with amendments to draft agreements and these are being finalised – these countries have nominated NCs and NPMs Guatemala is responding with queries that are being processed Cambodia and Sri Lanka are processing agreements through their respective systems – these countries have yet to nominate NCs and NPMs

## Slide 5: Next steps and actions taken (3)
Next steps | Actions taken
Participating countries establish agreements with development partners regarding contributions and support (e.g. international costs, in-country costs and activities) OECD to confirm with development partners agreements for support to the project – general contributions and country-specific contributions | Senegal has established agreements with the World Bank and France (AFD). Zambia has established agreements with the World Bank and DFID Sri Lanka and Cambodia are in the process of establishing agreements with the World Bank OECD has signed grant agreements with Norway (Norad), UK (DFID), Germany (BMZ/GIZ) and Korea

## Slide 6: Next steps and actions taken (4)
Next steps | Actions taken
OECD to collate information regarding capacity-building experiences, specifically regarding student assessment and use of results | ToR and plans for a high level report on the experiences of non-OECD countries participating in PISA prepared and agreed with the World Bank. High level report to be launched at the end of 2014 and to inform peer-to-peer learning activities in 2015, 2016 and 2017 Capacity needs analysis completed for Ecuador, Senegal and Zambia. Capacity needs analysis planned for Sri Lanka in May, Guatemala in June and Cambodia in July Capacity building programmes designed for all participating countries by October 2014

## Slide 7: Next steps and actions taken (5)
Next steps | Actions taken
OECD to confirm with other agencies arrangements for technical partnerships and collaboration | Technical partnerships and collaboration established with UIS and UNICEF on OOSC Dialogue continued with PASEC, SACMEQ and LLECE with a view to establishing technical partnerships and collaboration by the end of 2014 Tor for a review of assessment programmes prepared and agreed with World Bank – work to be commissioned Contributions to LMTF, education in the post-2015 agenda and EFA through UNESCO Collaboration with EFA GMR

## Slide 8: Next steps and actions taken (6)
Next steps | Actions taken
First meetings of International Steering Group and Technical Advisory Group (including capacity-building) | The first meeting of the International Advisory Group is scheduled for 27-28 May. The agenda will include: ToRs for the IAG and election of co-chairs; the main technical challenges based on the first set of technical papers; ToRs for the TAG and selection of members; capacity needs analysis of participating countries, the design of capacity building programmes and the status of project implementation plans; engagement and communication strategy, plans for peer-to-peer learning; ToR for the International Contractor(s); project implementation timeline; proposal for an independent review of the project. First meeting of the TAG planned for November 2014, following appointment of IC(s)

## Slide 9: PISA participants
Contribute to international costs of Euros 200,000
Benefit from a survey focused on three domains of learning and can opt for additional domains
Findings inform policy and practice
Facilitates benchmarking, target setting, analysis of what works to improve learning outcomes
Learning from policies and practices applied elsewhere
Included in international reports by the OECD ( “performance league tables”)

## Slide 10: PISA for Development participants
Receive results on students performance in reading, mathematics and science (if data adjudicated) comparable to international PISA results
Country-specific report drafted jointly with the OECD based on the policy-priorities of the country – publication of results at discretion of participant
Includes information regarding out-of-school youth – quantitative and descriptive regarding potential policy-levers
Benefit from country-specific capacity-building programme designed to ensure country has technical and institutional capacity to implement PISA and beyond
Benefit from specially designed peer-to-peer learning opportunities focused on learning from policies and practices applied elsewhere
Provide input and guidance for how to enhance PISA instruments, methods and analyses
Knowledgeable and well prepared for entry into future PISA cycles
International cost of Euros 583,000 for each country

## Slide 11: Next steps (7)
Tendering process to commission international contractor (s) by OECD
Project implementation:
Design, planning and coordination (including capacity assessment, capacity building planning for participating countries and project implementation plans);
Technical development
Field trials and main data collection;
Analysis and reporting
Post-pilot governance

## Slide 12: PISA for Development: Prospective Timeline – Meetings & Phases
Notes:
The five phases of the project will, in reality, overlap with each other.
The final phase, post-pilot governance, will extend beyond the project.
There is scope for holding additional meetings of the International Steering Group and Technical Advisory Group if these are required.

## Slide 13: PISA for Development: Initial Implementation Schedule