## Slide 1: PISA for Development
Technical Workshop
Draft Components of ToRs
10th October 2014
OECD Secretariat

## Slide 2: Strand C: Defining cohort assessment in-school and out-of-school
Requirements
The bidder is required to collaborate with Strand A and B on all aspects of the project.
Bidders should clearly state what is their definition of in and out of school considering that presence in school is a process, not a dichotomy.
The bidders should propose how they are going to work with Strands A and B to ensure the coverage of the 15 year old cohort, in-school and out-of-school.
The successful bidders will have to agree with relevant national authorities and the international contractor for Strand A on a definition for in-school and out-of-school that is standardised and consistent across countries. As part of this, in each country it will be necessary to determine and agree which alternative programmes, if any, count as equivalent to being in school. The bidders should therefore explain in their proposals how they propose to determine and agree these definitions and to standardise them across the countries.
Strand A contractor takes leadership of the assessment process (review and decisions on Strand A and B will be taken by the time that Strand C contractor is selected. We need to clarify where degrees of freedom are and where constraints and key decisions are made and contractors should comply with-Idea is that Strand C contractor will work within the framework set by Strand A contractor-Idea of a checklist).
The successful bidder will need to liaise with the Contractor for Strand B regarding how the contextual questionnaires for Strand C will be sufficiently detailed and comprehensive to capture the whole range of Non-Formal Education (NFE) and be cleared with the national authorities.
The successful bidder should explain how they are going to approach 15 year olds from the perspective of the household rather than the school.

## Slide 3: Strand C: Counting and locating 15 year olds (1)
Requirements
Bidders should work with countries and explain how they are going to search for any additional information about 15 year olds and how they might go about exploring identified discrepancies.
Bidders should work with countries to collect information about people with special education needs and minority groups, however defined, in innovative ways, and allocate resources and time to review existing surveys of the disabled and of minority groups.
Where there are large discrepancies in the population estimates between data collected by and reported to international organisations and DHS surveys, the Bidders should dedicate resources and time to analyse appropriate national data. Special attention should be paid to the problems of inter-censal migration and of missing groups. Bidders should adjust the estimates to take account of omissions from household surveys. The suggestion for generating adjusted numbers should be discussed with national committees.

## Slide 4: Strand C: Counting and locating 15 year olds (2)
Constraints
Population (census-based) data may be quite out-of-date. Household survey data are limited in their coverage of marginal or vulnerable groups.
Questions
Based on the target population agreed with each country, are there any other possible methodological approaches for counting and locating 15 year olds and developing rules for constructing a sampling frame?
What are the implications for the approach to sampling, interviewing and testing if the age bracket is extended to 14 to 16? What are the cost implications?
How will the bidder approach situations where the age of an individual is uncertain because, for example, there are no official records available or because even the individual or their care giver is uncertain about his or her age?

## Slide 5: Strand C: Towards constructing a sampling frame for 15 year olds (1)
Requirements
Bidders should explain their parameters to construct a sample and, if they are going to design a probability sample, specify whether and how they are going to collaborate with the contractor for Strand A. Bidders should propose a concrete sample size and spell out in detail the assumptions made to estimate the proposed sample size.
Bidders should discuss with the country on the stratification approach (….to re-word).
Bidders should discuss the pros and cons of each approach to sampling. The two main options to compare and discuss are: (i) to list all households reporting a 15 year old in the household and then arrange an appointment to interview them subsequently; and (ii) to record both precise age and school attendance status at the same time. Bidders should make their own evaluation.
The bidders should include suggestions as to how to control for potential biases and how this possible bias could be monitored or minimised.

## Slide 6: Strand C: Constructing a sampling frame for 15 year olds (2)
Requirements (Continued)
Bidders should propose options for the following: modes/approaches/strategies for interviewing; contents of interviews; and the management of the interview encounter for interviewing in urban slums / informal settlements, for the household and non-household populations and for those with special education needs.
Research priorities should be discussed with the countries.
Bidders should understand the sample size for strand A and propose (strive for?) at least a minimum number of 200-400 (to discuss) responses per item (cognitive and contextual).
To add discussion on CI (to discuss)?
Although there is no such thing as a perfect survey, bidders should suggest ways in which they will calculate/document omissions from the sampling frame and the extent of possible biases as a consequence of those omissions.

## Slide 7: Strand C: Constructing a sampling frame for 15 year olds (3)
Constraints
Bidders should present a feasible plan for household listing.
This pilot project should provide a methodology to assess the extent of census - household survey discrepancies and offer suggestions for appropriate adjustments.
Bidders should adopt a mini-census prior to full scale interviewing and testing. This approach has issues and limitations that bidders should discuss. In particular, they should elaborate on issues of refusal and of over- or under-identification of 15 year olds.

## Slide 8: Constructing a sampling frame (4)
Constraints
If bidders propose to adopt citizen volunteers as interviewers and testers, they must provide a detailed and comprehensive plan for administering a training programme.
If bidders identify the need to survey children in settings other than the household, like business, farms, or religious institutions/communities, they should propose a systematic approach to sampling from different sizes and types of settings.
Special arrangements for surveying non-household populations would almost certainly have to be locally context specific.

## Slide 9: Strand C: Constructing a sampling frame for 15 year olds (5)
Questions
What are the viable options to conduct household surveys of 15 year olds from a variety of socio-demographic settings?
With Strand A, what are the strategies to guarantee that the PISA cohort of 15 year olds is fully surveyed?
What could be the challenges of adapting the survey instruments to marginalised/minority (ethnic, language, religious, etc.) populations and how would you address them?
How can the cognitive and contextual instruments accommodate multiple languages and cultural references/sentitivities in one location?

## Slide 10: Strand C: Surveying, administering an interview and testing 15 year olds in the household (1)
Requirements
There should be a close collaboration with the contractors for Strand A in the development of the cognitive component.
Bidders should explain how they are going to match information from different sources about the age of the child.
Bidders should explain how to handle recruitment, selection and training of country-specific teams.
Bidders should explore the option of administrating the questionnaire and the test via other modes of delivery, such as the mobile phone and other mobile device. Contractors need to elaborate on of the impact of the mode of delivery on the performance on the test.

## Slide 11: Strand C: Surveying, administering an interview and testing 15 year olds in the household (2)
Questions
How do bidders propose to deal with inconsistencies of sources of information about the age of the child?
How do bidders propose to ensure maximum participation and minimum withdrawal and non-response?
Can incentives be an option? For whom?
Do bidders plan on using other modes of delivery, such as mobile phones? If so, what portions of the assessment could be done over the phone? How would this choice impact the comparability of results with other PISA tests?

## Slide 12: Strand C: Surveying, administering an interview and testing 15 year olds in the household (3)
Constraints/challenges
Clarifying age and status of 15 year olds:
  The bidders should strive to define unambiguously the age of children and their ‘at school’ or ‘out-of-school’ status. However, flexibility of the age range and considerations on the fluidity of the in and out of school status are recommended.
Recruiting, selecting and training mini-census-takers and interviewers:
Bidders are to explore and explain quality assurance mechanisms. In particular, parts of the cognitive assessment will contain items from protected item banks. Bidders should explain how they will ensure the confidentiality and security of the tests.
To protect themselves and the quality of the assessment, interviewers should work in pairs.

## Slide 13: Strand C: Surveying, administering an interview and testing 15 year olds in the household (4)
Constraints/challenges (continued)
The interviewers may face a variety of spoken languages in each household.
Approaching and interviewing 15 year-olds in their settings:
The interview and test are, in most cases, probably best administered at home because that is where most of the out-of-school 15 year olds will be living and working.
Street children and others will have to be interviewed and tested where they can be found.

## Slide 14: Strand C: Designing and developing assessment and analytical frameworks and instruments for household PISA (1)
Requirements
Bidders should state their preferred approach and the resources needed for designing the complementary assessment frameworks and instruments required. They should also make proposals for management and content of the core cognitive and contextual assessments.
Bidders should provide justification of the various options/choices based on their advantages and disadvantages.
Bidders should explain how they are going to develop the conceptual assessment and analysis framework and whether it would build on those developed for Strands A and B or developed separately but clearly identifying linkage points.
Bidders should explain how they will develop the modular structure of the assessment, including what levels of literacy will be tested for each of the options in the cognitive assessment (including the use of reading and numeracy components) and the main themes and target populations for each of the modules included in the contextual questionnaires.
The modifications proposed to the contextual questionnaire have to provide similar material across the participating countries. Specific attention should be paid to the applicability of the contextual questionnaire to marginal and vulnerable groups, for example, the level of language complexity used in the questioning.
Bidders should consider the design of country specific options in the contextual questionnaire/s.
Bidders should detail their approach to designing and piloting the out-of-school assessment and to what extent it will be possible to provide comparable material across countries and the in and out-of-school assessments.

## Slide 15: Strand C: Designing and developing assessment and analytical frameworks and instruments for household PISA (2)
Requirements (Continued)
Bidders should present a detailed account of the various sources of contextual information and justify their choices of best informants. They should also explore the role of interviewers in data gathering.
Bidders should identify the 15 year old as the primary respondent.
Bidders should suggest approaches for capturing information on the community where the household is located (add and elaborate on this).
Bidders should present a theoretical framework that justifies the specificities of the contextual assessment for 15 year olds from Strand C.
Bidders should specify a baseline cost for a core assessment (child in household-in community context) and describe additional costs or savings associated to the assessment of parents and caregivers, principals, and community leaders.
Bidders should describe what arrangements – and costs - they envisage for interviewing in minority languages and populations with special needs.
Bidders should propose the optimum duration of the tests and contextual questionnaires.
In their proposals, bidders should indicate how they plan on incorporating secondary data from other sources in the direct contextual assessment.

## Slide 16: Strand C: Designing and developing assessment and analytical frameworks and instruments for household PISA (3)
Requirements (Continued)
The proposals should contain detailed descriptions of how the bidders decide to approach and capture non‐school-based learning opportunities.
The contextual assessment should include working activities and work-based skill assessment.
Bidders should explain how they plan on accounting for potential divides between language at home and school and language of communication within the household, or with care-givers.
In the bids, there should be a theoretical and practical description of how social and infrastructural resources in the community will be assessed in interaction with the life learning processes and in relation to school access, permanence, and transition.
Bidders are invited to consult the expert paper for Strand B by Willms and Tramonte (2014); they should justify their choices of using the same approach to measure poverty and extreme poverty or substantiate their proposal to measure poverty and extreme poverty by means of other, different items and indicators.

## Slide 17: Strand C: Designing and developing assessment and analytical frameworks and instruments for household PISA (4)
Constraints
The assessment of living and learning environment may require the administration of different contextual questionnaires, layered with the results of direct observation and administrative data.
Whenever interviewed, respondents should be asked questions that are formulated with a vocabulary appropriate for grade 5 and below. Also, interviewers may experience a variety of languages, and therefore need translators.
The core of the contextual assessment should be consistent across countries and possibly across strands. The possibility to create a modular component for Strand C should be considered in synergy with Strand B and this will involve the following challenges:
  Capturing and describing non‐school-based learning opportunities (examples must be listed in here to explain what is non school based).
  Including working activities and work-based skill assessment.

## Slide 18: Strand C: Designing and developing assessment and analytical frameworks and instruments for household PISA (5)
Constraints (Continued)
Accounting for potential divides between language at home and school (the problem posed by that divide is among the primary causes of school drop‐out) and language of communication within the household.
Assessing social and infrastructural resources in the community.
Measuring extreme poverty.
Accounting for non‐household based living arrangements.
In some circumstances, e.g. interviewing street children, it may be necessary for interviewers to work in pairs.
The contextual questionnaires should be short, effective and simple to administer.
The contextual questionnaires should adapt to a variety of languages and reading/comprehending skills as well as to potential forms of disability.

## Slide 19: Strand C: Designing and developing assessment and analytical frameworks and instruments for household PISA (6)
Questions
What collaboration arrangements will the bidder make with other interested assessment institutions (including ASER, LAMP, PIAAC, PASEC and SACMEQ)?
Which elements of the assessment (cognitive and contextual) will be comparable across countries and which ones will be country specific?

## Slide 20: Strand C: Additional requirements
Requirements in developing manuals
Bidders, if successful, should expect to follow the models/templates of the current PISA models/standards when it comes to preparing manuals in support of Strand C.
The manuals to be developed by contractors and sub-contractors should include considerations of meeting place, sensitivity and timing.
Drafts of the manuals and standards will be submitted by the international contractor for Strand C to the OECD PISA Secretariat for checking and approval with reference to the International Advisory Group.

## Slide 21
Add assets in the contextual questionnaire
Add an analysis plan